## Sheet1
Section | Correction | Difficulty | Status | Page | Para No | Comments
Chapter 7 -Simulations | Base line of WSN sending straight to processing | Red
| Rerun all scenarios with additional scenarios | Red
| Formalise description of experiment | Red | Done | 7.2 onwards | All
| Error bars on graphs | Amber |  |  |  | See email but errors are very small when using SE
| Keep figures with text | Green | Done | All Chap 7 | All
| Remove claims about energy usage | Green | Done | All Chap 7 | All
Chapter 4- K-HAS | Separate out architecture design from scenario | Amber | Done |  |  | This may not be separate enough?
| Make explicit the DA will be running on a desktop | Green | Done | 67 | 2 | Should this be reiterated in the LORIS chapter?
| Compare to OGC-SWE | Amber | Done | 89 | 2, 3
Image Classification | Clarify role of image processing and use of templates | Amber | Done | 55, 86 | 1, 2
| Distinguish between interesting and species level | Amber | Done | 55 | 3, 4
| Clearly state what has been implemented | Red | Done | 55, 81, 86 | -
| How would templates be matched? | Amber | Done | 55
| Provide link to Triton source | Green | Done | 53
| Correct definition for accuracy | Amber | Done | 53 |  | Redefined accuracy
| Make clear drools requires specialist knowledge | Green | Done | 78
| Show how a rule could be added to drools | Green | Done | 86
| Architecture needs UML diagrams | Red | Done | 70
Ontology | Correction of claims in Chapter 5 | Amber | Done | 91 | -
| Correction of claims in Chapter 8 | Amber | Done | 150 | -
| SSN is sensor and obs centric | Amber | Done | 98 | 2
| Introduce SUMO as general purpose | Amber | Done | 99 | 2
| Remove claim about modularity | Amber | Done | - | -
| Discussion on why SSN does not fit needs | Red | Done | 101 | 2 | Is this enough detail?
Local Knowledge | Correct and move to appropriate chapter | Amber | Done | 59 | 1
| Combine 2 plots | Amber | Done | 46 | Fig 3.5
| Separate out UK wet and dry (provide values) | Amber | Cannot Do | - | - | Do not have values
| Include values for when DGFC loses signal | Green | Cannot Do | - | - | Cannot find values
General Comments | Remove LK and GK | Green | Done |  | - | Also removed from acronyms
| Provide more than one citation for multiple tools | Amber |  |  |  | Examples?
| Don't use the term scientific observation | Amber | Done? |  | - | Is this for all uses? Some observations referred to are not ecological, those have been corrected
| Remove et al from references | Green | Done | - | -
| Provide map of field centre | Amber | Done | 37 | Fig 3.2
| Remove claims about UK and Malaysian similarities | Green | Done | 49 | -
| Field names in 4.3 do not match | Green | Done | 69 | Fig 4.3
| Make Findings 5.1.2 a subheading | Green | Done | 100 | 2
| Cite all cameras | Green | Done | 120 | 3 | Few exist so few were looked at
| Provide picture of Buckeye case | Green | Done | 121 | Fig 6.1
| State why only 2 pics | Green | Done | 124 | 1
| Remove setting of scientific name in 6.4 | Green | Done | 129 | Listing 6.1
| State number or rules used in LORIS | Amber | Done | 133 | 2
| Indicate which part of interview | Amber | Done | 131 | 1
| Rewrite para about global/local knowledge | Amber | Done | 131 | 2 | Needs checking
| Citations for Weka and J48 | Amber | Done | 133 | 2 | Citation for decision tree not showing
Minor Corrections/Typos | Throughout Thesis | Amber | Done | - | -